|  |  |  |
| --- | --- | --- |
| Week | |  |
| 1 | 01/09/2025  07/09/2025 | Date: 01/09/2025  Time: 10:45 – 12:45  Present: Pablo, Rico, Pieter, Fleur  Absent: None  Tasks done:   * Listening to introduction lectures and companies. All |
| 2 | 08/09/2025  14/09/2025 | Date: 09/09/2025  Time: 10:45 – 12:45  Present: Pablo, Rico, Pieter, Fleur  Absent: None  Tasks done:   * Get acquainted with the group. All * Getting familiar with the company. All * Getting familiar with the kind of data the measure. All |
| 3 | 15/09/2025  21/09/2025 | Date: 16/09/2025  Present: Pablo, Rico, Fleur  Time: 13:45 – 15:45  Absent: Pieter (sick)  Tasks done:   * Making a planning. Pablo, Rico, Fleur * Collecting necessary documents. Fleur * Collecting the data. Rico   Tasks:   * Formulating the research question and creating the problem definition. Pieter * Opening the data. Pablo * Data scanning and visualization. Rico * Contacting the TAs. Fleur * Making the logbook. Fleur |
| 4 | 22/09/2025  28/09/2025 | Date: 23/09/2025  Time: 10:00 – 10:30  Present: Pablo, Rico, Fleur, Harald, Diogo (online), Mahnam (online)  Absent: Pieter  Tasks done:   * Clarify the project. * Collecting more data. * Planning the midterm. |
| 4 | 22/09/2025  28/09/2025 | Date: 23/09/2025  Time: 13:45 – 15:45  Present: Pablo, Rico, Pieter, Fleur  Absent: None  Tasks done:   * Checking the research question. All * Formulate sub research questions. All * Checking the problem definition. Fleur * Formulating the dataset. Rico * Formulating the current planned tech stack. Pieter   Tasks:   * Making plots of all measurements in one dataframe. Rico * Making plots in different weight frames. Pablo * Making a scatterplot of all the data. Fleur * Making the follow up code. Pieter |
| 5 | 29/09/2025  05/10/2025 | Date: 30/09/2025  Time:  Present: Rico, Pieter, Fleur  Absent: Pablo (out)  Tasks done:  Tasks: |
| 6 | 06/10/2025  12/10/2025 | Date: 07/10/2025  Time:  Present: Pablo, Rico, Pieter, Fleur  Absent:  Tasks done:  Tasks: |
| 6 | 06/10/2025  12/10/2025 | Date: 09/10/2025  Time:  Present: Pablo, Rico, Pieter, Fleur  Absent:  Tasks done: Midterm in Best  Tasks: |
| 7 | 13/10/2025  19/10/2025 | Date: 14/10/2025  Time:  Present: Pablo, Rico, Pieter, Fleur  Absent:  Tasks done:  Tasks: |
| 8 | 20/10/2025  26/10/2025 | Date: 21/10/2025  Time:  Present: Pablo, Rico, Pieter, Fleur  Absent:  Tasks done:  Tasks: |
| 9 | 27/10/2025  02/11/2025 | Date: 28/10/2025  Time:  Present: Pablo, Rico, Pieter, Fleur  Absent:  Tasks done:  Tasks: |
| 10 | 03/11/2025  09/11/2025 | Date: 03/11/2025  Time:  Present: Pablo, Rico, Pieter, Fleur  Absent:  Tasks done:  Tasks: |