## Blad1
[7 empty] | Planning meetings every Tuesday at 1 pm | [11 empty] | Mails: | F.C.Cauwels@student.tudelft.nl | Fleur Cauwels
[7 empty] | Additional weekly update meeting: some Mondays and Thursdays (text, online or on-campus) | [12 empty] | R.J.deJong-4@student.tudelft.nl | Rico de Jong
[20 empty] | P.W.Paap@student.tudelft.nl | Pieter Paap
[20 empty] | psotoscrespo@student.tudelft.nl | Pablo Sotos
Date | 01.Sep | 03.Sep | 09.Sep | 11.Sep | 16.Sep | 18.Sep | 23.Sep | 25.Sep | 30.Sep | 02.Oct | 07.Oct | 09.Oct | 14.Oct | 16.Oct | 21.Oct | 23.Oct | 28.Oct | 29.Oct | 04.Nov
Week | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | Done when | Responsible | Priority
Task/Sprint
Keep in track of the planning | [19 empty] | Complete backlog | Fleur/Pablo | 1
Choosing the project | [19 empty] | Assigned to a project | All | 2
Create Wiki (Github) | [19 empty] | Wiki created | Rico/Fleur | 3
Getting familiar with the company | [19 empty] | Know what the company does | All | 4
Collect the test data | [19 empty] | Test data colleted | Rico | 5
Visulize the test data | [19 empty] | Plots were made | Pieter | 6
Formulate the goal of the project | [19 empty] | Formulated the problem definition | Pieter/Fleur | 7
Formulate the RQ | [19 empty] | Have a main and sub RQ's | All | 8
Collect the data 1 | [19 empty] | Data is colleted (3500 files) | Rico | 9
Fromulate the tech stack | [19 empty] | Have the complete tech stack | Pieter | 10
Data processing | [19 empty] | Data cleaned | Pieter/Rico | 11
Coding the visualization | [19 empty] | Have clear plots | Pieter | 12
Choose the visualization | [19 empty] | Clear which visualization to use | Pieter/Rico | 13
Prepare midterm 1 | [19 empty] | Have a pp | Fleur | 14
See how the robot works in real life | [19 empty] | Visiting Smart Robotics offices | Fleur/Rico/Pieter | 15
Midterm1 presentation | [19 empty] | Midterm1 presentation | All | 16
Collect the data 2 | [19 empty] | More Data is colleted (30000 files) | All | 17
Formulate the data set | [19 empty] | Have the complete data set | Rico | 18
Reseach on different ML methodes | [19 empty] | List of possible ML | Rico/Pieter | 19
Classfication of the expected weight | [19 empty] | Results and visualization | Pablo | 20
Coding ML | [19 empty] | Results of ML applied in the data | Pieter | 21
Validation | [19 empty] | Accuracy ok | Pieter/Rico | 22
Answer all the RQs | [19 empty] | All RQs are answer | All | 23
Evaluation | [19 empty] | Accuracy ok | Pieter | 24
Clean the code | [19 empty] | Code is easy readable | Pieter/Rico | 25
Write the data story | [19 empty] | List of possible data story | All | 26
Write and produce data story | [19 empty] | Data story done | All | 27
Update the Wiki (GitHub) | [19 empty] | Wiki updated | All | 28
Fixing code errors | [19 empty] | Code errors are fixed | Pieter | 29
Estimation of doublepicks | [19 empty] | Doublepicks are found | Pieter/Rico | 30
Creating the portfolio (GitHub) | [19 empty] | Portfolio is made (GitHub) | All | 31
Create presentation | [19 empty] | Pp is made | All | 32
Pitch | [19 empty] | Pitch is written | All | 33