## Blad1
Date | 01.Sep | 03.Sep | 09.Sep | 11.Sep | 16.Sep | 18.Sep | 23.Sep | 25.Sep | 30.Sep | 02.Oct | 07.Oct | 09.Oct | 14.Oct | 16.Oct | 21.Oct | 23.Oct | 28.Oct | 30.Oct | 04.Nov
Week | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | Done when | Responsible | Priority
Task/Sprint
Choosing the project | [19 empty] | Assigned to a project | All | 1
Keep in track of the planning | [19 empty] | Complete backlog | Fleur/Pablo | 2
Getting familiar with the company | [19 empty] | Know what the company does | All | 3
Collect the test data | [19 empty] | Test data colleted | Rico | 4
Visulize the test data | [19 empty] | Plots were made | Pieter | 5
Formulate the goal of the project | [19 empty] | Formulated the problem definition | Pieter/Fleur | 6
Formulate the RQ | [19 empty] | Have a main and sub RQ's | All | 7
Collect the data 1 | [19 empty] | Data is colleted (3500 files) | Rico | 8
Collect the data 2 | [19 empty] | More Data is colleted (30000 files) | All | 9
Formulate the data set | [19 empty] | Have the compleet data set | Rico | 10
Fromulate the tech stack | [19 empty] | Have the complete tech stack | Pieter | 11
Data processing | [19 empty] | Data deaned |  | 12
Choose the visualization | [19 empty] | Clear which visualization to use |  | 13
Coding the visualization | [19 empty] | Have clear plots | Pieter | 14
Prepare midterm 1 | [19 empty] | Have a pp | Fleur | 15
See how the robot works in real life | [19 empty] | Visiting Smart Robotics offices | Fleur/Rico/Pieter | 16
Midterm1 presentation | [19 empty] | Midterm1 presentation | All | 17
Reseach on different ML methodes | [19 empty] | List of possible ML | Rico/Pieter | 18
Classfication of the expected weight | [19 empty] | Results and visualization | Pablo | 19
Coding ML | [19 empty] | Results of ML applied in the data | Pieter | 20
Validation | [19 empty] | Accuracy ok |  | 21
Answer all the RQs | [19 empty] | All RQs are answer |  | 22
Evaluation | [19 empty] | Accuracy ok |  | 23
Clean the code | [19 empty] | Code is easy readable |  | 24
Search for data story | [19 empty] | List of possible data story |  | 25
Write and produce data story | [19 empty] | Data story done |  | 26
Creating the portfolio | [19 empty] | Portfolio is made |  | 27
Create presentation | [19 empty] | Pp is made |  | 28
Pitch | [19 empty] | Pitch is written |  | 29