## Blad1
Date | 01.Sep | 03.Sep | 09.Sep | 11.Sep | 16.Sep | 18.Sep | 23.Sep | 25.Sep | 30.Sep | 02.Oct | 07.Oct | 09.Oct | 14.Oct | 16.Oct | 21.Oct | 23.Oct | 28.Oct | 30.Oct | 04.Nov
Week | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | Done when | Responsible | Priority
Task/Sprint
Choosing the project | [19 empty] | Assigned to a project | All | 1
Keep in track of the planning | [19 empty] | Complete backlog | Fleur/Pablo | 2
Create Wiki (Github) | [19 empty] | Wiki created | Rico/Fleur | 3
Getting familiar with the company | [19 empty] | Know what the company does | All | 4
Collect the test data | [19 empty] | Test data colleted | Rico | 5
Visulize the test data | [19 empty] | Plots were made | Pieter | 6
Formulate the goal of the project | [19 empty] | Formulated the problem definition | Pieter/Fleur | 7
Formulate the RQ | [19 empty] | Have a main and sub RQ's | All | 8
Collect the data 1 | [19 empty] | Data is colleted (3500 files) | Rico | 9
Collect the data 2 | [19 empty] | More Data is colleted (30000 files) | All | 10
Formulate the data set | [19 empty] | Have the complete data set | Rico | 11
Fromulate the tech stack | [19 empty] | Have the complete tech stack | Pieter | 12
Data processing | [19 empty] | Data cleaned | Pieter/Rico | 13
Coding the visualization | [19 empty] | Have clear plots | Pieter | 14
Choose the visualization | [19 empty] | Clear which visualization to use | Pieter/Rico | 15
Prepare midterm 1 | [19 empty] | Have a pp | Fleur | 16
See how the robot works in real life | [19 empty] | Visiting Smart Robotics offices | Fleur/Rico/Pieter | 17
Midterm1 presentation | [19 empty] | Midterm1 presentation | All | 18
Reseach on different ML methodes | [19 empty] | List of possible ML | Rico/Pieter | 19
Classfication of the expected weight | [19 empty] | Results and visualization | Pablo | 20
Coding ML | [19 empty] | Results of ML applied in the data | Pieter | 21
Validation | [19 empty] | Accuracy ok | Pieter/Rico | 22
Answer all the RQs | [19 empty] | All RQs are answer | All | 23
Evaluation | [19 empty] | Accuracy ok |  | 24
Clean the code | [19 empty] | Code is easy readable | Pieter/Rico | 25
Update the Wiki (GitHub) | [19 empty] | Wiki updated | All | 26
Write the data story | [19 empty] | List of possible data story |  | 27
Write and produce data story | [19 empty] | Data story done |  | 28
Creating the portfolio | [19 empty] | Portfolio is made |  | 29
Create presentation | [19 empty] | Pp is made |  | 30
Pitch | [19 empty] | Pitch is written |  | 31